ZITO SUPER APP PHASED IMPLEMENTATION PLAN PRD v10 ULTIMATE ¦ NestJS + Prisma + PostgreSQL + Next.js CONFIDENTIAL ¦ VG Global Logistics ¦ April 2026

# Implementation Overview

The ZITO platform is divided into 5 phases. Each phase builds on the previous one, allowing you to go live with core features first and add advanced capabilities over time. The schema is already complete — all phases share the same database.

| Phase | Theme | Timeline | Modules | Outcome |
| --- | --- | --- | --- | --- |
| Phase 1 | Core Platform | Weeks 1-6 | 9 modules | App live — users can book & pay |
| Phase 2 | Warehouse & Inventory | Weeks 7-11 | 7 modules | Full warehouse & scan ops live |
| Phase 3 | Finance & Billing | Weeks 12-15 | 7 modules | Full billing, invoicing & B2B ready |
| Phase 4 | Intelligence Layer | Weeks 16-20 | 8 modules | Fraud, surge, route AI, heatmap |
| Phase 5 | Scale & Africa-Ready | Weeks 21-26 | 6 modules | Multi-country, offline, marketplace |

BACKEND = NestJS/Prisma API work   FRONTEND = Next.js/React UI work   BOTH = Backend + Frontend   SCHEMA = Already done (Prisma)

PHASE 1 Core Platform — Go Live Auth · Users · Bookings · Drivers · Fleet · Payments · Notifications · Support · Agency

Goal: Ship the minimum viable platform. Customers can register, book a trip, pay, and track it. Drivers receive jobs and update status. Admins manage everything.

## 1.1 Authentication & Users (PRD §2, §3, §4)

The foundation. Nothing else works without this.

| Task | File | Type |
| --- | --- | --- |
| auth module — login, OTP, JWT, refresh token | auth.module.ts, auth.service.ts, auth.controller.ts | BACKEND |
| OTP flow — send, verify, rate limit, cooldown | strategies/jwt.strategy.ts, dto/ | BACKEND |
| User registration + KYC document upload | users.module.ts, users.service.ts | BACKEND |
| Account lifecycle — PENDING → VERIFIED → ACTIVE | users.controller.ts, kyc-upload.dto.ts | BACKEND |
| Login page, Register page, OTP verify page | (auth)/login, register, verify-otp, pending-approval | FRONTEND |
| Role selection screen (multi-role support) | select-role/page.tsx | FRONTEND |
| JWT guard, roles guard, RBAC decorators | common/guards/, common/decorators/ | BACKEND |

## 1.2 Agency Setup (PRD §31)

Required early because Bookings reference agencyId.

| Task | File | Type |
| --- | --- | --- |
| Agency CRUD — create, update, list, deactivate | agencies.module.ts, agencies.service.ts | BACKEND |
| Agency controller with RBAC (Super Admin only) | agencies.controller.ts | BACKEND |
| Staff management — roles, permissions, login | staff.module.ts, staff.service.ts, staff.controller.ts | BACKEND |
| Admin agency dashboard | (admin)/agencies/ | FRONTEND |

## 1.3 Booking Engine (PRD §6)

Core revenue driver. Full lifecycle from PENDING → COMPLETED.

| Task | File | Type |
| --- | --- | --- |
| Create booking — multi-stop, serviceType, pricing | bookings.service.ts — create() | BACKEND |
| Full status lifecycle with audit log at every step | bookings.service.ts — updateStatus() | BACKEND |
| Cancellation with reason + refund policy logic | bookings.service.ts — cancel() | BACKEND |
| Idempotency key enforcement on booking create | idempotency.interceptor.ts | BACKEND |
| Admin booking list, assign driver, override status | bookings.controller.ts (Admin routes) | BACKEND |
| Customer booking list + detail + cancel | (customer)/bookings/ pages | FRONTEND |
| New booking flow — 3-step wizard (vehicle/route/confirm) | (customer)/bookings/new/ | FRONTEND |
| Admin bookings dashboard with filters | (admin)/bookings/page.tsx | FRONTEND |

## 1.4 Driver System (PRD §8, §44.1, §44.2)

| Task | File | Type |
| --- | --- | --- |
| Driver profile — create, GPS update, online/offline toggle | drivers.service.ts | BACKEND |
| Driver matching engine — proximity, rating, availability | drivers.service.ts — matchDriver() | BACKEND |
| Shift system — start/end shift, hours calc (DONE) | shift/shift.service.ts | BACKEND |
| ShiftActiveGuard — block bookings without active shift | shift/shift-active.guard.ts | BACKEND |
| Payroll engine — trip earnings, incentives, penalties | payroll/payroll.service.ts | BACKEND |
| Driver dashboard — jobs list, accept/reject trip | (driver)/dashboard, (driver)/jobs/ | FRONTEND |
| Shift control screen — start/end shift button | (driver)/shift/page.tsx | FRONTEND |
| Earnings screen — wallet balance, payout history | (driver)/earnings/page.tsx | FRONTEND |

## 1.5 Fleet & Vehicle (PRD §9)

| Task | File | Type |
| --- | --- | --- |
| Vehicle CRUD — add, edit, assign to driver | fleet.module.ts, fleet.service.ts | BACKEND |
| Insurance / permit expiry tracking with alerts | fleet.service.ts — checkExpiry() | BACKEND |
| Dual GPS tracking — driver mobile vs vehicle device | fleet.service.ts — updateGps() | BACKEND |
| Breakdown reporting and rescue flow | breakdown/breakdown.service.ts | BACKEND |
| Transporter fleet dashboard | (transporter)/fleet/, (transporter)/drivers/ | FRONTEND |
| Admin fleet overview | (admin)/fleet/page.tsx | FRONTEND |

## 1.6 Payment & Wallet (PRD §15)

| Task | File | Type |
| --- | --- | --- |
| Initiate payment — M-Pesa STK push integration | payments/mpesa/mpesa.service.ts | BACKEND |
| Escrow — hold on booking, release on delivery | payments/escrow/escrow.service.ts | BACKEND |
| Wallet — credit/debit with idempotency keys | payments/wallet/wallet.service.ts | BACKEND |
| Payment retry logic without duplicate transactions | payments.service.ts — retry() | BACKEND |
| Automated refund on cancellation | payments.service.ts — refund() | BACKEND |
| Customer payment history screen | (customer)/payments/page.tsx | FRONTEND |
| Admin payment dashboard + manual reconcile | (admin)/payments/page.tsx | FRONTEND |

## 1.7 Notifications (PRD §22)

| Task | File | Type |
| --- | --- | --- |
| SMS channel — Africa's Talking integration | notifications/channels/sms.service.ts | BACKEND |
| Email channel — SendGrid / Resend integration | notifications/channels/email.service.ts | BACKEND |
| Push channel — Firebase FCM | notifications/channels/push.service.ts | BACKEND |
| Retry + fallback — SMS fail → Email → Push | notifications.service.ts | BACKEND |
| Booking events — created, assigned, delivered, paid | notifications.service.ts — trigger() | BACKEND |

## 1.8 Real-Time Tracking (PRD §26)

| Task | File | Type |
| --- | --- | --- |
| WebSocket gateway — driver location broadcast | tracking/tracking.gateway.ts | BACKEND |
| Customer tracking endpoint — ETA + live location | tracking/tracking.service.ts | BACKEND |
| Live map component — driver pin + ETA display | components/maps/LiveMap.tsx | FRONTEND |
| Customer tracking page | (customer)/tracking/[bookingId]/page.tsx | FRONTEND |
| Socket.io client hook | hooks/useSocket.ts | FRONTEND |

## 1.9 Support Tickets (PRD §25, §36)

| Task | File | Type |
| --- | --- | --- |
| Create ticket — linked to booking, categories, priority | support.service.ts — create() | BACKEND |
| Ticket lifecycle — OPEN → IN_PROGRESS → RESOLVED | support.service.ts — updateStatus() | BACKEND |
| Customer support page — raise & track ticket | (customer)/support/page.tsx | FRONTEND |
| Staff support panel — view, assign, resolve | (staff)/support/page.tsx | FRONTEND |

## Phase 1 Deliverables Checklist

- Users can register, verify OTP, upload KYC, await approval

- Customers can create bookings (multi-stop, cargo details, vehicle type)

- Admin can assign driver, track status, override anything

- Drivers receive job notifications, start/end shift, update trip status

- M-Pesa payment works with escrow hold and release

- Live GPS tracking visible to customer

- Support tickets can be raised and resolved

- All actions logged in AuditLog

PHASE 2 Warehouse & Inventory Warehouse · Zones · Inventory · Scan · Waybills · Loss Detection · RTO

Goal: Full warehouse operations — inbound, storage, dispatch, scan at every checkpoint. Loss detection and return (RTO) system active.

## 2.1 Warehouse Management (PRD §10)

| Task | File | Type |
| --- | --- | --- |
| Warehouse CRUD — create, zones, racks, bins | warehouses.module.ts, warehouses.service.ts | BACKEND |
| Capacity tracking — real-time availability per zone | warehouses.service.ts — getCapacity() | BACKEND |
| Multi-agency warehouse sharing control | warehouses.service.ts — agencyFilter() | BACKEND |
| Warehouse dashboard — zones, rack map, occupancy | (warehouse)/dashboard/page.tsx | FRONTEND |
| Bin management UI | (warehouse)/bins/page.tsx | FRONTEND |

## 2.2 Inventory System (PRD §11)

| Task | File | Type |
| --- | --- | --- |
| Inventory item CRUD — parcelId, owner, weight, fragile | inventory.service.ts — create() | BACKEND |
| FIFO / FEFO dispatch priority logic | inventory.service.ts — getDispatchOrder() | BACKEND |
| Ownership segregation — multi-client per warehouse | inventory.service.ts — filterByOwner() | BACKEND |
| Movement history — full trail per item | inventory.service.ts — addMovement() | BACKEND |
| Inventory list + item detail page | (warehouse)/inventory/page.tsx | FRONTEND |

## 2.3 Scan System (PRD §12)

Rule: No scan = No movement. Every checkpoint requires a scan event.

| Task | File | Type |
| --- | --- | --- |
| Scan event creation — item + checkpoint + GPS + driver | scan.service.ts — record() | BACKEND |
| Scan validation — block movement if scan missing | scan.service.ts — validate() | BACKEND |
| Vehicle load mapping — parcel must be linked to vehicle | scan.service.ts — loadToVehicle() | BACKEND |
| OTP / delivery proof capture at delivery checkpoint | scan.service.ts — confirmDelivery() | BACKEND |
| Offline scan queue with sync-on-reconnect | hooks/useOfflineSync.ts | FRONTEND |
| Barcode scanner UI component | components/scan/BarcodeScanner.tsx | FRONTEND |
| Warehouse scan screen | (warehouse)/scan/page.tsx | FRONTEND |

## 2.4 Waybill / LR System (PRD §14)

| Task | File | Type |
| --- | --- | --- |
| Waybill creation — linked to booking + parcels | waybills.service.ts — create() | BACKEND |
| LR for FTL, Waybill for PTL/Courier type routing | waybills.service.ts — assignType() | BACKEND |
| Audit lock — is_locked = true, no edits after close | waybills.service.ts — lock() | BACKEND |
| Waybill PDF generation for driver manifest | waybills.service.ts — generatePdf() | BACKEND |

## 2.5 Loss Detection (PRD §13, §44.6)

| Task | File | Type |
| --- | --- | --- |
| Batch mismatch detection — expected vs scanned count | loss-detection.service.ts — detectMismatch() | BACKEND |
| Stale item alerts — no movement within SLA window | loss-detection.service.ts — detectStale() | BACKEND |
| Loss report — type, photo proof, estimated value | loss-detection.service.ts — createReport() | BACKEND |
| Dual approval for high-value claims | loss-detection.service.ts — requireApproval() | BACKEND |
| Loss report list — admin + warehouse staff | (admin)/loss-detection/page.tsx | FRONTEND |

## 2.6 Return / RTO System (PRD §44.5)

| Task | File | Type |
| --- | --- | --- |
| RTO initiation — delivery failed → return triggered | rto.service.ts — initiate() | BACKEND |
| RTO lifecycle — IN_TRANSIT → WAREHOUSE_RECEIVED → CLOSED | rto.service.ts — updateStatus() | BACKEND |
| RTO linked back to warehouse for receiving | rto.service.ts — receiveAtWarehouse() | BACKEND |

## 2.7 Fuel Management (PRD §44.3)

| Task | File | Type |
| --- | --- | --- |
| Fuel log per trip — expected vs actual vs variance | fleet/fuel/fuel.service.ts | BACKEND |
| Abnormal usage alert — variance threshold trigger | fleet/fuel/fuel.service.ts — detectTheft() | BACKEND |
| Fuel log report for admin / transporter | (admin)/fleet/page.tsx (fuel tab) | FRONTEND |

PHASE 3 Finance & Billing Rate Cards · Invoices · B2B Contracts · SLA · Reconciliation · Audit · Admin Controls

Goal: Full financial layer. Invoices auto-generate, B2B clients get credit billing, payment reconciliation runs daily, admin actions require approval for high-risk operations.

## 3.1 Rate Card System (PRD §19)

| Task | File | Type |
| --- | --- | --- |
| Rate card CRUD — vehicle type, serviceType, base/km/stop rate | rate-cards.service.ts | BACKEND |
| Dynamic pricing — distance × rate + base + surges | rate-cards.service.ts — calculate() | BACKEND |
| Version history — every change logged with old/new values | rate-cards.service.ts — versionLog() | BACKEND |
| Admin rate card management UI | (admin)/rate-cards/page.tsx | FRONTEND |

## 3.2 Invoice & Billing (PRD §16, §17, §18)

| Task | File | Type |
| --- | --- | --- |
| Auto invoice generation on trip/warehouse completion | invoices.service.ts — generate() | BACKEND |
| Invoice types — Transport, Warehouse, Courier, Combined | invoices.service.ts — assignType() | BACKEND |
| Audit lock — is_locked = true prevents edits after issue | invoices.service.ts — lock() | BACKEND |
| Dual approval for invoice modifications above threshold | invoices.service.ts — requestApproval() | BACKEND |
| Warehouse billing — space × days × rate formula | billing/billing.service.ts | BACKEND |
| Multi-service combined invoice for corporate clients | billing/billing.service.ts — consolidate() | BACKEND |
| Customer invoice list + download PDF | (customer)/invoices/page.tsx | FRONTEND |
| Corporate outstanding invoices + credit usage | (corporate)/invoices/page.tsx | FRONTEND |
| Admin invoice approval dashboard | (admin)/invoices/page.tsx | FRONTEND |

## 3.3 B2B Contract System (PRD §20)

| Task | File | Type |
| --- | --- | --- |
| Contract CRUD — credit limit, billing cycle, payment terms | contracts.service.ts | BACKEND |
| Credit enforcement — block booking if limit exceeded | contracts.service.ts — checkCredit() | BACKEND |
| Corporate portal — bookings, invoices, contracts | (corporate)/ pages | FRONTEND |

## 3.4 SLA System (PRD §21, §44.10)

| Task | File | Type |
| --- | --- | --- |
| SLA timers — configurable per service type | sla.service.ts — startTimer() | BACKEND |
| Delay detection and alert escalation | sla.service.ts — detectBreach() | BACKEND |
| Escalation flow — Level 1 → Level 2 → Manager → Super Admin | sla.service.ts — escalate() | BACKEND |
| Driver no-show auto-reassign trigger | sla.service.ts — handleNoShow() | BACKEND |

## 3.5 Payment Reconciliation (PRD §35, §44.12)

| Task | File | Type |
| --- | --- | --- |
| Invoice vs payment auto-match using reference IDs | reconciliation.service.ts — autoMatch() | BACKEND |
| Mismatch detection — amount / duplicate / missing | reconciliation.service.ts — detectMismatch() | BACKEND |
| Daily reconciliation report generation | reconciliation.service.ts — dailyReport() | BACKEND |
| Admin reconciliation dashboard | (admin)/reconciliation/page.tsx | FRONTEND |

## 3.6 Admin Control System (PRD §44.14)

High-risk actions require approval before execution.

| Task | File | Type |
| --- | --- | --- |
| Approval workflow — refunds, payout override, booking cancel | audit/audit.service.ts — requireApproval() | BACKEND |
| Dual authorization for financial operations | audit/audit.service.ts — dualApprove() | BACKEND |
| Admin action control dashboard | (admin)/audit/page.tsx | FRONTEND |
| Staff performance metrics — bookings, tickets, resolution time | staff-performance.service.ts | BACKEND |
| Staff performance dashboard | (admin)/staff-performance/page.tsx | FRONTEND |

## 3.7 Analytics (PRD §27A, §27B)

| Task | File | Type |
| --- | --- | --- |
| Revenue analytics — daily/monthly, by service, by agency | analytics.service.ts — revenue() | BACKEND |
| Driver performance — completion rate, rating, on-time % | analytics.service.ts — driverKpis() | BACKEND |
| Warehouse utilization — %, dwell time, turnover | analytics.service.ts — warehouseKpis() | BACKEND |
| Customer retention — CLV, repeat rate, NPS | retention.service.ts | BACKEND |
| Promo codes, loyalty points, referral program | retention.service.ts — promos() | BACKEND |
| Admin analytics dashboard | (admin)/analytics/page.tsx | FRONTEND |

PHASE 4 Intelligence Layer Fraud · Surge Pricing · Route Optimization · Heatmap · Capacity Planning · Alerts · Health

Goal: Make the platform smart. Automated fraud detection, dynamic surge pricing, AI-assisted route optimization, driver demand heatmap, and system health monitoring.

## 4.1 Fraud Detection (PRD §44.7)

| Task | File | Type |
| --- | --- | --- |
| GPS spoof detection — driver vs vehicle position delta | fraud.service.ts — detectGpsSpoof() | BACKEND |
| Ghost trip detection — trip with no scan events | fraud.service.ts — detectGhostTrip() | BACKEND |
| Duplicate booking detection — idempotency key check | fraud.service.ts — detectDuplicate() | BACKEND |
| Abnormal route detection — deviation from planned route | fraud.service.ts — detectRouteAnomaly() | BACKEND |
| Fraud flag dashboard + account suspension controls | (admin)/fraud/page.tsx | FRONTEND |

## 4.2 Surge Pricing (PRD §44.8)

| Task | File | Type |
| --- | --- | --- |
| Demand/supply ratio calculator per zone | surge-pricing.service.ts — calcRatio() | BACKEND |
| Zone-based surge activation with multiplier | surge-pricing.service.ts — activateZone() | BACKEND |
| Peak-hour surge rules — time-based config | surge-pricing.service.ts — peakHourRules() | BACKEND |
| Emergency surge override by Super Admin | surge-pricing.controller.ts — override() | BACKEND |
| Surge zone map in admin dashboard | (admin)/rate-cards/page.tsx (surge tab) | FRONTEND |

## 4.3 Route Optimization (PRD §44.17)

| Task | File | Type |
| --- | --- | --- |
| Shortest path calculation — Google Maps Directions API | route-optimization.service.ts — calculate() | BACKEND |
| Multi-stop sequence optimization | route-optimization.service.ts — optimizeStops() | BACKEND |
| Route deviation alerts — driver went off route | route-optimization.service.ts — detectDeviation() | BACKEND |
| Dynamic recalculation on traffic / road block | route-optimization.service.ts — recalculate() | BACKEND |
| Map component with route display | components/maps/LiveMap.tsx (route layer) | FRONTEND |

## 4.4 Driver Demand Heatmap (PRD §44.21)

| Task | File | Type |
| --- | --- | --- |
| Zone demand calculation — active bookings vs drivers | heatmap.service.ts — calcDemand() | BACKEND |
| Real-time heatmap data endpoint for driver app | heatmap.controller.ts | BACKEND |
| Zone threshold config — low / medium / high intensity | heatmap.service.ts — setThresholds() | BACKEND |
| Driver heatmap screen — move-to-zone suggestions | (driver)/heatmap/page.tsx | FRONTEND |
| Heatmap layer component | components/maps/HeatmapLayer.tsx | FRONTEND |

## 4.5 Capacity Planning (PRD §44.18)

| Task | File | Type |
| --- | --- | --- |
| Warehouse capacity tracking — real-time occupancy % | capacity-planning.service.ts — warehouse() | BACKEND |
| Fleet availability tracking — vehicles online vs total | capacity-planning.service.ts — fleet() | BACKEND |
| Overbooking prevention — block if capacity full | capacity-planning.service.ts — enforceLimit() | BACKEND |
| Demand forecasting — historical trend analysis | capacity-planning.service.ts — forecast() | BACKEND |

## 4.6 Internal Alert System (PRD §39)

| Task | File | Type |
| --- | --- | --- |
| Alert triggers — missing parcel, payment failure, delay, fraud | alerts.service.ts — trigger() | BACKEND |
| Alert routing — warehouse mgr, accounts, dispatch, super admin | alerts.service.ts — route() | BACKEND |
| Low warehouse capacity alert — >90% occupancy | alerts.service.ts — capacityAlert() | BACKEND |
| Driver offline during active trip alert | alerts.service.ts — driverOfflineAlert() | BACKEND |
| Admin alerts dashboard | (admin)/alerts/page.tsx | FRONTEND |

## 4.7 System Health Monitoring (PRD §44.11)

| Task | File | Type |
| --- | --- | --- |
| API failure rate monitoring + alert | Integrate with Sentry / Datadog | BACKEND |
| Database performance monitoring | Prisma query logging + slow query alerts | BACKEND |
| Queue failure alerts — BullMQ dead letter queue | BullMQ event listeners | BACKEND |
| Uptime monitoring — health check endpoint | /health endpoint with DB + Redis check | BACKEND |
| System health dashboard | (admin)/system-health/page.tsx | FRONTEND |

## 4.8 Session & Access Control (PRD §44.15)

| Task | File | Type |
| --- | --- | --- |
| Auto logout after inactivity — configurable timeout | common/guards/session.guard.ts | BACKEND |
| Forced logout by Super Admin — invalidate all tokens | auth.service.ts — forceLogout() | BACKEND |
| Device tracking + IP logging on every login | auth.service.ts — logSession() | BACKEND |
| Suspicious login detection — new device / IP alert | auth.service.ts — detectSuspicious() | BACKEND |
| Re-authentication for critical actions | common/decorators/reauth.decorator.ts | BACKEND |

PHASE 5 Scale & Africa-Ready Offline Mode · Multi-Currency · Marketplace · Partner Onboarding · USSD · Multi-Country

Goal: Expand beyond Kenya. Offline-capable operations for low-connectivity areas, multi-currency billing, third-party marketplace for transporters/warehouses, and USSD fallback for feature phones.

## 5.1 Offline Mode (PRD §23)

| Task | File | Type |
| --- | --- | --- |
| Offline scan queue — store locally, sync on reconnect | hooks/useOfflineSync.ts | FRONTEND |
| Conflict resolution — latest valid scan wins | scan.service.ts — resolveConflict() | BACKEND |
| Duplicate scan detection and merge/reject | scan.service.ts — deduplicateScan() | BACKEND |
| Offline map caching — tiles stored for low-connectivity | components/maps/ — offline cache | FRONTEND |
| Retry with exponential backoff on API failures | lib/api.ts — retryInterceptor() | FRONTEND |

## 5.2 Multi-Currency & Multi-Language (PRD §23)

| Task | File | Type |
| --- | --- | --- |
| Currency support — KES, UGX, TZS, NGN, GHS, ZAR | config/app.config.ts — currencies | BACKEND |
| Currency conversion at rate card calculation | rate-cards.service.ts — convertCurrency() | BACKEND |
| Swahili + French + Amharic language packs | frontend i18n config — next-intl | FRONTEND |
| Language selector in user profile | (customer)/profile/page.tsx | FRONTEND |

## 5.3 Marketplace / Aggregator Mode (PRD §44.20)

| Task | File | Type |
| --- | --- | --- |
| Third-party transporter onboarding + verification | marketplace.service.ts — onboardTransporter() | BACKEND |
| Warehouse partner onboarding + approval workflow | marketplace.service.ts — onboardWarehouse() | BACKEND |
| Bidding system — fixed price vs open bid vs negotiation | marketplace.service.ts — bid() | BACKEND |
| Commission tracking per marketplace transaction | marketplace.service.ts — calcCommission() | BACKEND |
| Partner performance monitoring + suspension controls | marketplace.service.ts — monitorPartner() | BACKEND |
| Marketplace partner dashboard | (admin)/marketplace/ pages | FRONTEND |

## 5.4 Partner Onboarding System (PRD §50)

| Task | File | Type |
| --- | --- | --- |
| Driver referral system — referrer gets bonus on activation | retention.service.ts — driverReferral() | BACKEND |
| Bulk fleet onboarding for transporter companies | fleet.service.ts — bulkOnboard() | BACKEND |
| Onboarding funnel analytics — registered → verified → active | analytics.service.ts — funnelReport() | BACKEND |
| Incentive joining bonus management | drivers/incentives/incentives.service.ts | BACKEND |

## 5.5 Multi-Country Expansion (PRD §49)

| Task | File | Type |
| --- | --- | --- |
| Multi-region deployment — Uganda, Tanzania, Rwanda | Infrastructure: multi-region Render/AWS | BACKEND |
| Country-specific rate cards and tax rules | rate-cards.service.ts — countryConfig() | BACKEND |
| Cross-border shipment tracking and agency handoffs | tracking.service.ts — crossBorderHandoff() | BACKEND |
| Inter-agency billing for cross-agency shipments | billing.service.ts — interAgencyBill() | BACKEND |

## 5.6 USSD Fallback (PRD §23)

| Task | File | Type |
| --- | --- | --- |
| USSD menu tree — book, track, pay via feature phone | Africa's Talking USSD API integration | BACKEND |
| Session management for USSD multi-step flows | USSD session store in Redis | BACKEND |
| SMS confirmation for USSD-initiated bookings | notifications/channels/sms.service.ts | BACKEND |

# Full Phase Summary

| Phase | Theme | Timeline | PRD Sections | What Gets Built |
| --- | --- | --- | --- | --- |
| 1 | Core Platform | Weeks 1-6 | §2,3,4,6,7,8,9,15,22,25,26,31,32 | Auth, booking engine, driver shifts, fleet, M-Pesa payments, escrow, live tracking, support tickets, notifications |
| 2 | Warehouse & Inventory | Weeks 7-11 | §10,11,12,13,14,44.3,44.5,44.6 | Warehouse zones/racks/bins, inventory FIFO/FEFO, scan system (no scan = no move), waybills, loss detection, RTO returns, fuel logs |
| 3 | Finance & Billing | Weeks 12-15 | §16,17,18,19,20,21,27A,27B,35,44.10,44.12,44.14,44.16 | Auto invoices, warehouse billing, B2B contracts & credit, SLA timers, escalation flow, payment reconciliation, analytics, staff performance |
| 4 | Intelligence Layer | Weeks 16-20 | §44.7,44.8,44.11,44.15,44.17,44.18,44.21,§39 | Fraud detection, surge pricing, route optimization, driver heatmap, capacity planning, internal alerts, system health, session security |
| 5 | Scale & Africa-Ready | Weeks 21-26 | §23,44.20,49,50 | Offline mode, multi-currency, multi-language, marketplace/aggregator, partner onboarding, multi-country deployment, USSD fallback |

DATABASE SCHEMA — COMPLETE (Phase 0) All 39 models are already in schema.prisma. No schema changes needed across any phase. Just add module code.